## Sheet1
Health | Primary | Start Date | End Date | % Completion
Project Information
Yellow | Project Plan | 2026-06-25 | 2026-07-01 | 60%
Green | Phase 1: Project Initiation & Data Exploration | 2026-07-05 | 2026-07-20 | 60%
Green | Discovery on pharmaceutical supply chain solutions & research | 2026-07-06 | 2026-07-17 | 100%
Green | Explore data sources and database constraints (5-year invoice ledger) | 2026-07-08 | 2026-07-24 | 80%
Green | Scope definition and final parameter mapping | 2026-07-09 | 2026-07-25 | 50%
Green | Phase:2 Literature review | 2026-06-20 | 2026-07-09 | 100%
Green | Research time-series & GBDT papers on Google Scholar / IEEE | 2026-06-21 | 2026-07-09 | 100%
Green | Research supply chain operationalization architectures | 2026-06-22 | 2026-07-09 | 100%
Blue | Phase:3 Requirements analysis & Design | 2026-07-25 | 2026-08-20 | 0%
Blue | Database initialization and ingestion schema configuration (SQL) | 2026-07-25 | 2026-08-05 | 0%
Blue | Prototype ETL logic—prioritize SKU-level description classifications | 2026-07-30 | 2026-08-10 | 0%
Blue | Prototype temporal flag mapping (Date vectors and QTY scaling parameters) | 2026-08-06 | 2026-08-16 | 0%
Blue | Prototype baseline exploratory tracking charts | 2026-08-15 | 2026-08-20 | 0%
Blue | Phase:4 Design | 2026-08-25 | 2026-09-05 | 0%
Blue | Design system context and automated data engineering pipeline diagrams | 2026-08-25 | 2026-08-30 | 0%
Blue | Model execution pipeline blueprint architecture | 2026-08-31 | 2026-09-05 | 0%
Blue | Phase:5 Development | 2026-09-06 | 2026-09-27 | 0%
Blue | Complete pipeline automation script assembly | 2026-09-06 | 2026-09-11 | 0%
Blue | Train and evaluate baseline time-series frameworks (SARIMA) | 2026-09-12 | 2026-09-18 | 0%
Blue | Program, evaluate, and cross-validate the supervised XGBoost Regressor | 2026-09-19 | 2026-09-25 | 0%
Blue | Interface creation (Power BI dashboard layer to visualize forecast variances) | 2026-09-25 | 2026-09-27 | 0%
Green | Phase:6 Documentation & Graded Deliverables | 2026-06-25 | 2026-10-01 | 10%
Green | Initial proposal draft compilation | 2026-06-25 | 2026-07-01 | 100%
Green | Final project proposal generation and layout assembly | 2026-07-01 | 2026-07-10 | 100%
Green | Chapter 1 (Introduction) and Chapter 2 (Literature Review) submission | 2026-06-20 | 2026-07-09 | 100%
Blue | Academic mid-point review evaluation and milestone review check | 2026-08-10 | 2026-08-10 | 0%
Blue | Final comprehensive report compilation and technical write-up | 2026-09-28 | 2026-09-28 | 0%
Blue | Viva voce presentation practice and final poster delivery | 2026-10-01 | 2026-10-01 | 0%